## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Amex
PROJECT: Milestone 4
Amex |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Andy | Mariana | Elicia | Xander
Project start date: | 2025-03-21 |  |  |  |  | March | [13 empty] | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2025-03-18 to 2025-05-12
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-03-18 to 2025-05-12
Expand on our screens | Milestone | All | 25% | 2025-03-18 | 7 | bar: 2025-03-18 to 2025-03-24
Design layout: Change Name | Low Risk | Elicia | 50% | 2025-03-18 | 4
Design layout: Change Password | Low Risk | Andy | 50% | 2025-03-18 | 4
Design layout: Change Picture | Low Risk | Xander | 50% | 2025-03-18 | 4
Design layout: Delete Account | Low Risk | Andy | 50% | 2025-03-18 | 4
Design layout: About us | Low Risk | Mariana | 50% | 2025-03-18 | 4
Design layout: Make a post | Low Risk | Mariana | 50% | 2025-03-18 | 4
Design layout: Get menu of the day | Low Risk | Xander | 50% | 2025-03-18 | 4
Design layout: Home Menu | Low Risk | Elicia | 50% | 2025-03-18 | 4
Add layout designs to android studio | Med Risk | Unassigned | 50% | 2025-03-21 | 3
Building App Functionality | Milestone | all | 0% | 2025-03-25 | 14 | bar: 2025-03-25 to 2025-04-07
Meet to assign tasks | Goal | all | 0% | 2025-03-25 | 1
Build account with login containing a username and password | High Risk | Unassigned | 0% | 2025-03-25 | 8
Build post making and feed within feed screen | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Build Menu viewing screen to connect to conco's menu | High Risk | Unassigned | 0% | 2025-03-25 | 8
Build home upload profile picture functionality | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Meet to merge progress or if behind discuss time needed | Goal | Unassigned | 0% | 2025-03-25 | 1 | 2025-03-25: 2
Build home feed with post making | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Build account setting Change username functionality | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Build account setting change password functionality | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Build post liking and disliking feature | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Build account setting change profile picture | Med Risk | Unassigned | 0% | 2025-03-25 | 8
Meet to merge progress or if behind discuss time needed | Goal | Unassigned | 0% | 2025-03-25 | 1
Testing | Milestone | all | 0% | 2025-04-01 | 8
Meet to assign tasks | Goal | Unassigned | 0% | 2025-04-01 | 1
Testing moving between screens | Low Risk | Unassigned | 0% | 2025-04-01 | 7
testing adding posts | Med Risk | Unassigned | 0% | 2025-04-01 | 7 | bar: 2025-04-01 to 2025-04-08
Testing change username and password functionality | Low Risk | Unassigned | 0% | 2025-04-01 | 7 | 2025-04-01: 2
Make sure the menu is correct | High Risk | Unassigned | 0% | 2025-04-01 | 7
TITLE 4 |  | Unassigned | 0% | 2025-04-01
To add more data, Insert new rows ABOVE this one
Formulas:
Mariana = IFERROR(IF(MIN(Milestones43524[Start])=0,TODAY(),B11(Milestones43524[Start])),TODAY())